## Schedule_Final
Zoho CRM Custom Report Widget · Development Schedule · Jun 9 – Jun 30 2026 · 3–4 hrs / day
# | ID | L1 | L2 | L3 | Phase / Task Group | Sub-Phase / Activity | Individual Task | Assignee | Status | Pct | Start | End | Notes / Definition of Done | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue
[11 empty] | Start | End |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1 | P0 | 0 | 0 | 0 | Phase 0 · Setup |  |  | All | Not Started | 0% | 2026-06-09 | 2026-06-10 | All parallel · Days 1-2 · 3.5 h each | bar: Tue 9 to Wed 10
2 | 0-1 | 0 | 1 | 0 |  | Environment & Custom Tab Setup |  | Lead | Not Started | 0% | 2026-06-09 | 2026-06-10 | 3 custom tabs + Sharing Rules=Private + widget stub | bar: Tue 9 to Wed 10
3 | 0-2 | 0 | 2 | 0 |  | Frontend Project Scaffold |  | Dev-B | Not Started | 0% | 2026-06-09 | 2026-06-10 | Vite+React18+MUI5 · ZOHO SDK PageLoad · zohoFunctions.js wrapper | bar: Tue 9 to Wed 10
4 | 0-3 | 0 | 3 | 0 |  | Deluge Dev Environment Setup |  | Dev-A | Not Started | 0% | 2026-06-09 | 2026-06-10 | 4 Deluge stubs · zoho.loginuser test · COQL smoke query | bar: Tue 9 to Wed 10
5 | P1 | 1 | 0 | 0 | Phase 1 · Backend Functions |  |  | Dev-A | Not Started | 0% | 2026-06-11 | 2026-06-22 | Sequential · Days 3-10 | bar: Thu 11 to Fri 12; Mon 15 to Fri 19; Mon 22
6 | 1-1 | 1 | 1 | 0 |  | get_my_report_settings.dg |  | Dev-A | Not Started | 0% | 2026-06-11 | 2026-06-11 | 3.5 h · fetch owned + shared presets; is_owner flag | bar: Thu 11
7 | 1-2 | 1 | 2 | 0 |  | save_user_report_setting.dg |  | Dev-A | Not Started | 0% | 2026-06-12 | 2026-06-12 | 3.5 h · create / overwrite + FORBIDDEN + INVALID_JSON | bar: Fri 12
8 | 1-3 | 1 | 3 | 0 |  | share_report_setting.dg |  | Dev-A | Not Started | 0% | 2026-06-15 | 2026-06-15 | 3.5 h · share + USER_NOT_FOUND + dedup user list | bar: Mon 15
9 | 1-4 | 1 | 4 | 0 |  | COQL Validation Engine |  | Dev-A | Not Started | 0% | 2026-06-16 | 2026-06-17 | 5 h · whitelist + JOIN limit ≤3 + page_size cap + large-module guard | bar: Tue 16 to Wed 17
10 | 1-5 | 1 | 5 | 0 |  | execute_custom_report.dg — COQL Builder & Executor |  | Dev-A | Not Started | 0% | 2026-06-18 | 2026-06-19 | 7 h · SELECT/WHERE/GROUP BY/LIMIT + dot-notation + pagination OFFSET | bar: Thu 18 to Fri 19
11 | 1-6 | 1 | 6 | 0 |  | Backend Code Review |  | Lead | Not Started | 0% | 2026-06-22 | 2026-06-22 | 2 h · security checklist · 9 unit-test sign-off | bar: Mon 22
12 | P2 | 2 | 0 | 0 | Phase 2 · Frontend Widget |  |  | Dev-B | Not Started | 0% | 2026-06-11 | 2026-06-24 | Parallel with Phase 1 · Days 3-12 | bar: Thu 11 to Fri 12; Mon 15 to Fri 19; Mon 22 to Wed 24
13 | 2-1 | 2 | 1 | 0 |  | App Root + SDK Integration + State Architecture |  | Dev-B | Not Started | 0% | 2026-06-11 | 2026-06-11 | 3.5 h · reportConfig / isStale / presets state · on-demand Execute | bar: Thu 11
14 | 2-2 | 2 | 2 | 0 |  | ModuleSelector.jsx |  | Dev-B | Not Started | 0% | 2026-06-12 | 2026-06-12 | 3.5 h · primary module + max 3 JOIN modules UI | bar: Fri 12
15 | 2-3 | 2 | 3 | 0 |  | FieldPicker.jsx |  | Dev-B | Not Started | 0% | 2026-06-15 | 2026-06-15 | 3.5 h · type badges + Lookup dot-notation + ordering | bar: Mon 15
16 | 2-4 | 2 | 4 | 0 |  | FilterBuilder.jsx |  | Dev-B | Not Started | 0% | 2026-06-16 | 2026-06-16 | 3.5 h · WHERE clause UI · operator per Data_Type | bar: Tue 16
17 | 2-5 | 2 | 5 | 0 |  | AggregationPanel.jsx |  | Dev-B | Not Started | 0% | 2026-06-17 | 2026-06-17 | 2 h · SUM / AVG / COUNT / MAX / MIN + GROUP BY panel | bar: Wed 17
18 | 2-6 | 2 | 6 | 0 |  | ResultTable.jsx + Copy Prevention |  | Dev-B | Not Started | 0% | 2026-06-18 | 2026-06-18 | 3.5 h · user-select:none + Ctrl+C block + loading skeleton | bar: Thu 18
19 | 2-7 | 2 | 7 | 0 |  | PaginationBar.jsx |  | Dev-B | Not Started | 0% | 2026-06-19 | 2026-06-19 | 2 h · Next Page button + has_more control | bar: Fri 19
20 | 2-8 | 2 | 8 | 0 |  | PresetList.jsx + SaveDialog.jsx |  | Dev-B | Not Started | 0% | 2026-06-22 | 2026-06-23 | 5 h · preset load / save / overwrite / share modal | bar: Mon 22 to Tue 23
21 | 2-9 | 2 | 9 | 0 |  | Frontend Code Review |  | Lead | Not Started | 0% | 2026-06-24 | 2026-06-24 | 2 h · copy-prevention verify + network-tab 0-call check | bar: Wed 24
22 | P3 | 3 | 0 | 0 | Phase 3 · Integration & Testing |  |  | Dev-A + Dev-B | Not Started | 0% | 2026-06-25 | 2026-06-26 | Days 13-14 · all parallel | bar: Thu 25 to Fri 26
23 | 3-1 | 3 | 1 | 0 |  | End-to-End Integration |  | Dev-A + Dev-B | Not Started | 0% | 2026-06-25 | 2026-06-25 | 3.5 h each · 3 LLD flows: Execute / Save-Share / Load-Run | bar: Thu 25
24 | 3-2 | 3 | 2 | 0 |  | Frontend Integration Tests |  | Dev-B | Not Started | 0% | 2026-06-26 | 2026-06-26 | 3.5 h · 6 test cases from LLD Sec 11 (copy, 0-call, Lookup…) | bar: Fri 26
25 | 3-3 | 3 | 3 | 0 |  | Backend Unit Tests |  | Dev-A | Not Started | 0% | 2026-06-26 | 2026-06-26 | 3.5 h · 9 unit-test cases from LLD Sec 11 | bar: Fri 26
26 | P4 | 4 | 0 | 0 | Phase 4 · Security Review & Deployment |  |  | Lead | Not Started | 0% | 2026-06-26 | 2026-06-30 | Days 14-16 | bar: Fri 26; Mon 29 to Tue 30
27 | 4-1 | 4 | 1 | 0 |  | Security Review |  | Lead | Not Started | 0% | 2026-06-26 | 2026-06-26 | 3.5 h · LLD Sec 9 full checklist sign-off | bar: Fri 26
28 | 4-2 | 4 | 2 | 0 |  | Widget Build & Production Deployment |  | Lead + Dev-B | Not Started | 0% | 2026-06-29 | 2026-06-29 | 2 h · npm build + deploy widget + activate 4 Deluge fns + smoke test | bar: Mon 29
29 | 4-3 | 4 | 3 | 0 |  | Admin Setup Guide |  | Lead | Not Started | 0% | 2026-06-30 | 2026-06-30 | 1.5 h · whitelist management doc for CRM admin | bar: Tue 30
Legend: |  |  | Lead |  | Dev-A (Backend) |  | Dev-B (Frontend) |  | Dev-A + Dev-B |  | Weekend